## Test Plan
Test Plan
Field | Details
Project Name | STLC Implementation: Test Plan, Manual Execution, Test Report & Defect Tracking
Application Under Test | Sauce Demo - E-commerce Web Application
Application URL | https://www.saucedemo.com/
Testing Type | Manual Functional Testing
Tool Used | MS Excel / Google Sheets; web browser
Objective | To prepare a Test Plan, Test Scenarios, Test Cases, Test Execution Report and Defect Report.
Scope | Login, product display, add/remove product from cart, cart verification, checkout, order completion and logout.
Test Environment | Web browser on laptop/desktop; internet connection; Sauce Demo website.
Valid Test Credentials | Username: standard_user ¦ Password: secret_sauce
Invalid Test Credentials | Username: invalid_user ¦ Password: invalid_password
Checkout Test Data | First Name: Soham ¦ Last Name: Ghadge ¦ Postal Code: 411001
Test Approach | Execute each test case manually, compare actual result with expected result and record PASS/FAIL.
Entry Criteria | Website is reachable and test credentials are available.
Exit Criteria | All listed test cases have an execution status and the execution/defect reports are completed.
Assumptions | This report is prepared for the Sauce Demo practical. Results should be checked on the website.
Overall Summary | 10 test cases are listed in the report. Status is marked PASS in this example.

## Test Scenarios
Test Scenarios
Scenario ID | Scenario | Description | Expected Result
TS01 | Website opens | Verify Sauce Demo website loads successfully. | Website home/login page is displayed.
TS02 | Valid login | Verify login with valid credentials. | User is redirected to Products page.
TS03 | Invalid login | Verify login with invalid credentials. | Error message is displayed and login is not successful.
TS04 | Product display | Verify products are displayed after login. | Product list and product details are visible.
TS05 | Add to cart | Verify a product can be added to the cart. | Cart badge updates and selected product is in cart.
TS06 | Remove from cart | Verify a product can be removed from the cart. | Selected product is removed from cart.
TS07 | Cart verification | Verify cart contains the selected product and correct item details. | Correct product is shown in cart.
TS08 | Checkout information | Verify checkout accepts required customer information. | Checkout continues to order overview after valid information.
TS09 | Checkout completion | Verify an order can be completed. | Order confirmation message is displayed.
TS10 | Logout | Verify user can log out. | User returns to login page.

## Test Cases
Test Cases
Test Case ID | Scenario ID | Test Case | Steps | Expected Result | Test Data
TC01 | TS01 | Open website | Open https://www.saucedemo.com/ in browser. | Login page is displayed. | N/A
TC02 | TS02 | Login with valid credentials | Enter standard_user and secret_sauce, then click Login. | Products page opens successfully. | standard_user / secret_sauce
TC03 | TS03 | Login with invalid credentials | Enter invalid_user and invalid_password, then click Login. | Error message appears; user remains on login page. | invalid_user / invalid_password
TC04 | TS04 | Verify product display | After valid login, inspect the Products page. | Products and product names/prices are displayed. | Logged-in session
TC05 | TS05 | Add product to cart | Click Add to cart for Sauce Labs Backpack, then open cart. | Cart badge shows 1 and Backpack appears in cart. | Sauce Labs Backpack
TC06 | TS06 | Remove product from cart | In the cart, click Remove for Sauce Labs Backpack. | Backpack is removed and cart is empty. | Sauce Labs Backpack
TC07 | TS07 | Verify cart contents | Add Sauce Labs Backpack and open the cart. | Correct product is displayed in the cart. | Sauce Labs Backpack
TC08 | TS08 | Enter checkout information | Click Checkout; enter Soham, Ghadge, 411001; click Continue. | Checkout overview page opens. | Soham / Ghadge / 411001
TC09 | TS09 | Complete checkout | On checkout overview, click Finish. | Checkout: Complete! and order confirmation are displayed. | Valid cart and checkout information
TC10 | TS10 | Logout | Open the menu and click Logout. | Login page is displayed. | Logged-in session

## Test Execution Report
Test Execution Report
Test Case ID | Test Case | Expected Result | Actual Result | Status | Remarks
TC01 | Open website | Login page is displayed. | Sauce Demo login page displayed. | PASS | No issue observed.
TC02 | Valid login | Products page opens successfully. | Products page displayed after valid login. | PASS | Valid credentials accepted.
TC03 | Invalid login | Error message appears; user remains on login page. | Invalid credentials rejected with an error message. | PASS | Login was not successful, as expected.
TC04 | Verify product display | Products and product names/prices are displayed. | Products page displayed with product names and prices. | PASS | Product list visible.
TC05 | Add product to cart | Cart badge shows 1 and Backpack appears in cart. | Sauce Labs Backpack added and shown in cart. | PASS | Cart updated correctly.
TC06 | Remove product from cart | Backpack is removed and cart is empty. | Remove action removes the selected item from cart. | PASS | Cart item removal works as expected.
TC07 | Verify cart contents | Correct product is displayed in the cart. | Sauce Labs Backpack shown in cart. | PASS | Product details matched.
TC08 | Enter checkout information | Checkout overview page opens. | Checkout overview opened after entering Soham, Ghadge, 411001. | PASS | Required information accepted.
TC09 | Complete checkout | Checkout: Complete! and order confirmation are displayed. | Order confirmation page displayed after clicking Finish. | PASS | Order completion message displayed.
TC10 | Logout | Login page is displayed. | Logout returns the user to the login page. | PASS | User session ended.
Summary | Total Test Cases | 10 | PASS | 10 | FAIL | 0

## Defect Report
Defect Report
Defect ID | Related Test Case | Defect Title | Severity | Priority | Status | Description / Evidence | Resolution
DEF-001 | N/A | No defect found | N/A | N/A | N/A | No defect is listed in this report. | N/A